APA CALIFORNIA BOARD

CONFERENCE REQUIREMENTS HANDBOOK

Amended

SEPTEMBER 2014

The following are requirements that each Conference must include as part of their conference planning.  This document outlines what the APA California Board of Directors expects of the Conference and the Conference Committee.  Areas not covered in this handbook are at the discretion of the VP of Conferences.

Table of Contents

#### I.	Getting Started		7

A.   Review & Incorporate APA California Conference Goals …………..….…….….….…………………….…..7

B.   Establish Site Selection Committee 	8

C.   Establish Conference Host Committee 	9

D.   Mandated Section Director Board Liaison & Other Chairs………….….........................................10

E.   Recommended Conference Host Committee Members/Chairs ..............................................11

II.	Consultants and Contracts	12

A.   Mandatory Use of Conference Consultants	12

B.   Conference Contract Review by APA California Attorney	12

III.	Establishing the Conference Budget	13

A.   V.P. of Conferences and V.P. of Administration Develops Budget	13	B.   Registration Fees	13

C.   Conference Expenses	13

D.   Board Approval of Conference Budget	13

E.   Conference Bank Accounts & Initial Advance	13

F.   Conference Sponsorships	14

G.   Conference Profits	14

H.  Profit Distribution	14

I.  Conference Losses	15

J.    1099 Tax Forms from Vendors 	15

K.   Additional Budget Considerations ……………………………………………………………………………………….15

IV.	Insurance and Risk Management	18

A.   Catastrophic Insurance	18

B.   Use of Chapter Liability Insurance	18

C.   Conference Activities Approved by APA California Attorney	18

D.   Association and Section Activity Guidelines	19

E.   Disability Inquiries & Complaints ……………………………….…………………………………………………..….19

V.	The Conference Program	19

A.   Conference Themes and Tracks	19

B.   Call for Presentations & Online Submission Forms	20

C.   Review Process for Session Selection	22

D.   Conference Session Notifications	26

E.   Organizing the Schedule and Slotting of All the Programs	27

F.   Conference Program Document 	32

G.   Session Recordings, Electronic Retention of Presentations, and the Mobile Applications	33

H. 	Certification Maintenance Credit 	33

I.   Mobile Workshops 	34

VI.	Advertising the Conference ................................................................................................... 35

A.   Cal Planner		35

B.   Section Newsletters	 36

C.   APA California Website – Conference Posting Process 	36

D.   Conference Website 	37

E.   E-Mails Directly to APA California Members 	37

#### VII.	Exhibit Booths/Display Space	37	A.   Complimentary & Contracted Display Space	37

#### VIII.	Other Mandatory Items 	38

A.   ADA Compliance & Notice in Registration Materials	38

B.   Reserve Hotel Rooms for APA California Board	38

C.   Extra Hotel Rooms	38

D.   Registration Confirmation	40

#### IX.	Mobile App		38

#### X.	At the Conference	39

A.   Thank the Conference Committee	39

B.   Head Table for APA California Board	39

C.   APA California Board Registration Packet Distribution	39

D.   Ribbons for Name Badges for Leadership and Speaker Identification	39

#### XI.	Standing Conference Committee	40

#### XII.	Updating and Distributing the Conference Handbook	41

- VP of Conferences	41

- Standing Conference Committee	41

- President and VP of Conferences	41

- APA California Board of Directors	41

#### Conference Handbook Timing Roadmap………………	…………42

#### Glossary of General and Conference Related Terms …………	…………..…….44

#### Appendices

A.   APA California and Section Legal and Insurance Activity Guidelines

B.   Conference Event Consultant Responsibilities

C.   Conference Account Management Consultant Responsibilities and Conference Financial Requirements

D.   Sample Conference Budgets [2011, 2012, & 2013]

E.   Conference Design and Publication Management Consultant

F.   Recommended Committee Structure/Roles and Responsibilities

G.  Conference Themes

H.   Evaluation Form for CM Sessions

I.    Sample Conference Closure Report

J.   Sample Forms/Templates

K.   Conference Site Selection Criteria

L.   Sustainability Principals

# I. GETTING STARTED

The APA California Conference is held every year in the fall, in the months of September, October, or November. The Conference typically commences on Saturday or Sunday, with a Student Conference Day including student awards luncheon, Diversity Summit during the day and an opening reception in the evening, and ends on Tuesday or Wednesday mid-day. The Statewide conference rotates among sections and the Sections serve as the “hosts.” However, it important that Sections keep in mind that they are partners with the Chapter and that the conference is for the benefit of APA California, local sections, and APA members as a whole.

While the conference is collaboration and joint team effort between the host Section and Chapter,  the Chapter is ultimately responsible for the conference's success in a variety of ways: the Chapter is responsible to APA National to provide a conference that contains sessions of interest to all segments of our membership and provides “creditworthy” learning experiences.  The Chapter is also responsible to the other Sections of APA California from a [public-relations or relationship perspective] as well as financially. Many sponsors and other organizations that participate in our conference do so from year to year. The Chapter must ensure that good relationships are maintained with others to enable those relationships to carry on. Also, revenue from one Section’s conference provides [significant] financial support to other Sections that next year. If profit is down or expenses misestimated, it affects not only the host Section and the Chapter, but all other Sections who are depending on annual revenue to assist their operations for the next year.  The host Section deservedly will be recognized publicly for the success of the conference.

The critical first steps include the review of the Conference Goals below, and formation of a site selection committee and host committee.  The committees can be two separate committees or one, whatever the Host Section prefers to do.

## REVIEW AND INCORPORATE APA CALIFORNIA CONFERENCE GOALS

It is important to keep in mind the purpose of the Conference at the beginning stages of the Conference, through the planning of the Conference, up to the date of the Conference itself.  Therefore the Board has adopted the overall Goals listed below that shall govern decision making by the VP of Conferences and Conference Host Committee.

The Conference shall:

- Provide continuing education for members.

- Provide AICP CM credits for all sessions and workshops.  Allowing AICP members to obtain a minimum of 16 CM credits.

- Provide networking opportunities.

- Provide dynamic, motivational, current and topical keynote speakers.

- Provide an atmosphere that is of high quality in all aspects of the Conference, including:

  - Conference Venue and Hotel

  - Opening Reception, Other Special Events and their Locations

  - Meals

  - Sessions

  - Mobile Workshops

  - Keynote Speakers.

  - Achieve the conference profit specified in F. on page 12.  Profits anticipated above the profit specified in F should be redirected by the Conference Host Committee (section) to increase the quality, and/or reduce the price to members, of the Conference and of Items 1-4 above.

  - Provide a conference that meets State adopted sustainability objectives as specified in Appendix J.

  - Encourage and allow flexible thinking and planning of the CHC each year, but ensure that basic aspects of planning the conference including provision of CM credits, budget of conference and key components, and others as specified in this Manual, need to work within the framework established by the Chapter to respond to expanding constituencies, respond to APA National, and contain costs.

## ESTABLISH SITE SELECTION COMMITtEE

Primary Responsibility:  The primary responsibility of the Site Selection Committee is to scout out potential city and hotel/conference locations within the Conference Host Section with the Conference Event Consultant. The committee shall consist of the VP of Conferences and the President Elect, Past President and the Section Director from the region being considered. The host section should refer to Appendix K to assist with selection of potential conference sites.

The Site Selection Committee must investigate alternative city/county sites and hotels and provide to the APA California Board information concerning at least two or three city/county and hotel alternatives along with the Site Selection Committee’s recommendation for the site they prefer.

Given the APA California goal of moving the conference around the State to each of the eight sections, it is also important to identify locations different than the last location the Section hosted the conference to entice members who like to attend conferences to get a new experience.

Time Frame:  The Site Selection Committee should be formed a minimum of 36 months prior to the estimated conference date.  Given the growing size of the state conferences over the past decade, it may be prudent to form the Site Selection Committee three years prior to the estimated conference date to allow the Committee time to find an adequate number of sites that meet the APA California requirements.

Factors to Consider in Site, Conference Facility, Hotel and Date Selection:  The Site Selection Committee shall attempt to select hotels that employ union employees and that are not the subject of a strike.  The conference hotel(s) must be ADA accessible.  In selecting the date for the conference, the Conference Committee must avoid conflicts with religious holidays, national holidays, and other conferences, including but not limited to the League of California Cities and County Supervisors Association of California (CSAC) conferences, and the National APA Fall Leadership Meetings.  In keeping with the APA California Board sustainability principals, the conference location should be accessible via several modes of transportation.

Board Approval for Site, Hotel, and Date:  The APA California Board shall approve the conference site (city/county and hotel) at a Board meeting or by e-mail Board vote.  Selection of the city/county and hotel must be made at least two years prior to the conference.

The APA California Board shall also approve the date selection at the same time as the site selection, and will review the conference profit amount each year at the time of the selection of the venue to ensure that sufficient conference profit can be realistically anticipated.

## ESTABLISH LOCAL CONFERENCE HOST COMMITTee (CHC)

A cohesive, well-organized, and unified Conference Host Committee will make all the difference as the host committee spends approximately two years planning the conference. Members of the CHC should be prepared to commit for the entire time the CHC is in existence: particularly important is the active involvement of all CHC members for the 12 months immediately preceding the conference.

The Host Section should utilize the Section’s website and newsletter to announce the formation of the Committee and the wealth of opportunities that exist for members to get involved in the preparation of the conference, including but not limited to assisting with mobile workshops, opening reception, volunteers and a portion of the programs/sessions.

- Select Conference Host Co-Chairs

Co-Chair Requirements:  The Conference Host Committee should appoint at least two co-chairs.  The goal is to have equal representation from both the public and private sectors, and ideally to have one co-chair from each sector.  However, it is more important to have capable co-chairs that have proven leadership and decision making skills. It is not advisable for the Conference Host Section Director to serve as a Conference co-chair. Rather the Section Director should be the liaison between the State and CHC.

Board Approval for Co-Chairs:  The Conference Host Section shall forward the names of the Co-Chair recommendations to the APA California Board for ratification. The recommendation shall include the individuals’ APA and professional experience.

2.	Recruit and Select Committee Chairs

The next step is for the Conference Host Committee Co-Chairs to select the Conference Committee Chairs.  It truly takes a community of local professional planners to organize, plan, and host a successful State Conference.  The mandated and recommended roles and responsibilities of the committees identified in this section are outlined below and in Appendix F.

- Recommended Conference Host Committee Members/Chairs:

- Programs Committee will also include 2-3 appointees to Chapter Session Selection Committee (assists with review and selection of Host section sessions), assists with selection of Keynotes, and assists with formation of session slots. It is critical to seek a Programs Committee Chair who has worked on a prior conference in some capacity. Also important for the Programs Chair is a general knowledge of prominent planners around the state who are likely to submit sessions or be called upon to assist in various ways with programs.

- Special Events/Opening Reception Committee (assists and coordinates with State and Conference Event Consultant)

- Local Sponsorship Committee (Sponsorships/Exhibitors-coordinates with VP Conferences/designee and Conference Event Consultant)

- Mobile Workshops Committee

- Volunteer Committee

- Student Programs Committee (work with the universities and Programs Committee to create a Student-only Day of Sessions and Student Poster Displays)

- Sustainability Committee (optional) coordinates with Conference Event Consultant and Conference facility to promote “green conference”

The VP of Conferences or designee will coordinate with the Conference Host Section Director to ensure formation of host committee chairs. The CHC shall also appoint a committee member to take minutes during the CHC meetings and provide meeting minutes to the CHC members, VP Conferences, Conference Event Consultant, and applicable conference. The CHC is also responsible to ensure the Conference Committee and conference contractors have accurate contact information for one another.  The CHC will include all conference contractors in the CHC meetings.

## MANDATED SECTION DIRECTOR/APA CALIFORNIA BOARD CONFERENCE LIAISON AND OTHER MANDATED COMMITTEE CHAIRS

- Section Director as Board Liaison

Duties:  The Section Director of the Conference Host Section will serve as liaison between the Conference Committee and the APA California Board and affiliated groups unless another Board member from the Host Section is specifically designated to serve as liaison.

Reports to Board:  The Chapter VP of Conferences will provide a conference update to the APA California Board at each Board meeting and on a monthly basis to the Executive Committee beginning one year prior to the conference date. This information is obtained from the Section Director of the Conference Host Section (Committee). Therefore, regular communication between the Section Director and VP Conferences is vital.

In addition, the Section Director of the Conference Host Section and the VP of Conferences will participate in all CHC monthly phone calls.  An update shall be prepared consisting of completing the Conference Timing Roadmap and Checklist at the end of the each month and submitting the most recent checklist to the APA California Board by e-mail as an attachment for the Board meetings as they occur.

The Section Director of the Conference Host Section shall also forward Conference Host Committee minutes to the VP of Conferences who will forward them to the APA California Board by e-mail if warranted and/or requested.

Conference Closure Report to Board:  The VP of Conferences in conjunction with the Conference Host Section Director shall provide the APA California Board with a Conference Closure Report at the January APA California Board meeting following the conference.  The Conference Closure Report shall include: Memo to the APA California Chapter Board which describes conference location, overall breakdown of attendees obtained from registration information and the Accounting Management Consultant, and highlights of what went well, identify issues/items which could have gone better, and suggestions for future Conferences. Also include as attachments: Profit/Loss and Balance Sheets for Conference obtained from the Accounting Management Consultant.

- VP of Public Information –this section could use updating

a.	Public Relations/Press Coordinator

Duties: The Chapter VP of Public Information and VP of Conferences shall be in charge of coordinating any press attending the conference.  The Conference Press Coordinator shall work with the APA California Public Relations Director/consultant so that the Conference Host Committee is aware of press invited and expected to attend the conference.  The VP of Public Information will coordinate with the Conference Event Consultant to also greet press attending the conference, prepare and provide them with session information, and guide them to the sessions or events they wish or were asked to attend. Coordination with CHC is highly encouraged. Media will not be allowed in ticketed events or meals unless they pay for the event.  Media passes will only be given to non-members.  See Appendix F for policy regarding press/media passes.

b.	Web Site Chair

Duties:  The Chapter VP of Public Information in coordination with the Conference Coordinator Consultant and the VP of Conferences shall have the overall responsibility to ensure that the Conference on the Chapter’s website is updated and populated and shall be authorized to update the Conference website.  However, any changes to the APA California Website or articles/announcements that will be featured on the APA California website homepage or other areas of the website shall be completed by Web Consultant.

## Recommended Conference Host Committee Members/Chairs

The following are recommended committees: Programs, Mobile Workshops, Special Events/Opening Reception, Local Sponsorship, Volunteer, Student Programs and Student Posters, Mobile App and Sustainability (optional). The Chapter VP of Conferences coordinates with the Conference Host Section Director to ensure formation of conference host committee chairs.

# II.	CONSULTANTS AND CONTRACTS

## MANDATORY USE OF CONFERENCE Consultants

As the size of the conferences has grown over the last decade, the APA California Board has determined the need to have consistency year to year and consistency between providers.  As a result, APA California has established contracts with providers who perform key tasks needed every year to reduce the burden on the CHC and provide consistency and efficiency from year to year. The following Chapter-contracted providers include but are not limited to::

1.	Conference Event Consultant/facility and venue items

2.	Conference Registrations and On-Site Registration Consultant

3.	Accounting Management Consultant

4.	Design/Graphics/Publication Consultant for print, web and mobile app projects.

5.	Web Consultant

6.	Mobile App Consultant

7.	CM /MCLE Credit Management Consultant

8.	Insurance Provider:  (The Conference Host Committee is required to coordinate for insurance through the APA California Board Director of Administration to ensure that the conference has the appropriate insurance coverage.  The Director of Administration will then contact the insurance provider.)

9. APA California Chapter Attorney

The APA California Board reserves the right to change consultants at any time.  All contracts with the consultants will be approved by the APA California Board and signed by the APA California President and the APA California attorney as to form. The conference contractors report to the VP Conferences.  A list of the current Conference Event Consultants, including contact information, can be found in Appendix B.

The names and contact information for each contracted consultant, their roles and responsibilities, and their relationships with both the conference committee and the APA California Board are articulated in Appendices B, C & E.

## CONFERENCE Contract Review by APA CALIFORNIA Attorney

All contracts for the conference other than those listed above, that are arranged by the VP of Conferences, designee or Conference Host Committee members, including those with facilities, off-site opening reception, transportation providers, and paid speakers shall be reviewed by the APA California attorney to ensure that indemnification and insurance clauses adequately protect APA California and the conference.

# III.  	ESTABLISHING THE CONFERENCE BUDGET

## VP of Conferences and VP of ADMINISTRATION Develops Budget

The VP of Conferences in consultation with the VP of Administration and Conference Host Committee Co-Chairs shall develop a preliminary conference budget. As noted below, all conference expenses shall be accounted for in the budget.  The budget shall detail anticipated revenues from registration fees, exhibitors, sponsorships, and any other revenue sources.  In addition, all anticipated expenses shall be detailed, including administration costs, special event costs, transportation, meals, vendors, publicity, reproduction, website, registration, and any other expenses. Sample budgets are provided in Appendix D (suggestion: use previous year’s final Profit and Loss Budget vs. Actual report as template).  The base attendee projection shall be 900 for urban areas and 600 for non-urban areas)

## Registration Fees

The amount of the registration fees shall be included in the budget and approved by the Board with the budget approval (See III.K.for information on setting the fees).

## Conference Expenses (also Financial Policy)

All conference expenses will be identified and monitored as part of the conference budget used by the CHC, and will not be identified as line items in the APA California budget, including Board contracted services.  Exceptions include those expenses directly related to the APA California Board meeting held during the conference and Pre-Conference Training [Note: both revenue and expenses for the Pre-Conference Trainings are Chapter budget items]. The conference host committee shall contact Accounting Management Consultant to determine the Board and Pre-Conference Training contracted line item expenses or seek clarification on this item.

## Board Approval of Conference Budget

The APA California Board shall review the preliminary conference budget for comment, and shall approve the final budget and profit estimate pursuant to F. (Conference Profits) below.  The budget approval shall be completed at a Board meeting or by e-mail Board vote.  The approved conference budget will then be used by Accounting Management Consultant to set up the conference financial reports and accounts.  Off-site or elaborate opening receptions, or other special events, must be approved by the APA California Board as part of the budget process.

## Conference BANK ACCOUNTS AND INITIAL CONFERENCE COMMITTEE advance (also Financial Policy)

The Accounting Management Consultant will maintain for the Chapter two conference checking accounts at all times. One will be used as the current conference account and the other for the conference for the following year.  Each account shall maintain a minimum balance of $15,000 that can be used as an advance by the conference committees to cover initial conference expenses.

## CONFERENCE SPONSORSHIPS

All sponsorship packages must be approved by the VP of Conferences and the APA California Chapter Board.  The sponsorship/exhibitor brochure template can be found in Appendix --.  The final page of the brochure will be the “about us” page, highlighting APA California, it’s mission and goals.  It should ablos include the attendee registration numbers from the previous 8 conferences.  Sponsorships shall be consistent from year to year, changes must be proposed and approved by the Board with the conference budget.

Conference Host Committee members will not receive sponsorships for "in-kind" services.  Participating in the CHC is voluntary and no member of the CHC shall be given preferential treatment for serving on the CHC.

All "In-Kind" sponsorships shall be approved by the VP of Conferences.

## Conference Profits (also Financial Policy)

The annual conference is a major revenue source for APA California and the eight Sections.  A profit of at least $100,000 should be achieved.  The Board will review the conference profit amount each year at the time of the selection of the venue to ensure that the amount keeps up with inflation and Chapter financial needs.

## CONFERENCE PROFIT DISTRIBUTION ( FINANCIAL POLICY ESTABLISHED 2011)

Before any profits are distributed to the Chapter, the Accounting Management Consultant will pay all conference expenses from gross conference revenues costs of accommodations and other bills associated with the conference, and the cost of all Board-contracted professional consultants. Following payment of conference expenses, the Accounting Management Consultant will disburse the net conference profits using the following formula:

| # Recipient | Percentage |
| --- | --- |
| APA CA | 40% |
| HOST SECTION | 40% |
| ALL OTHER SECTIONS | 20% |
| TOTAL | 100% |

## Conference Losses

In the event a conference falls below the $100,000 profit or loses money, the Board, at the next Board meeting or by phone vote, will determine how debts are to be paid or how percentage distributions shall be made Careful consideration will be given at this time to address hardship on sections highly dependent on conference profit revenue.

## 1099 Tax Forms From Vendors

Any 1099 tax forms sent to the Conference Host Committee by vendors shall be sent to the Accounting Management Consultant, at the address listed in Appendix C.

## Additional Budget Consideration

            - Complimentary Conference Registrations

Complimentary conference registrations must be provided prior to registration.

APA California Award Winners

All APA California award winners will be provided with one free admission to the awards ceremony and one meal.  Additional meals or one-day registration to sessions shall be available for purchase separately.

CPF Student Award Winners

The top winners of the CPF scholarship awards, including the Diversity Scholarship award winner, receive a free full student registration for the main conference.  (All students, including CPF scholarship award winners, receive free registration to the pre-conference Student Day)The CPF Board conference liaison shall contact the VP of Conferences to relay information about the CPF award winners.

Conference Session Speakers, Speaker Payment and Registration Fees

Except for professionals engaged as keynote speakers, conference speakers including session speakers are not paid. APA California Chapter does not provide complimentary registration in exchange for being a speaker at the conference. However, presenters (speakers other than keynotes) will receive a discounted registration fee if they wish to attend the conference.

Speakers/panelists who plan to present their session(s) and attend the conference must register for the conference at the discounted speaker registration rates for either the one day or full conference registration.

If speaker plans to attend the conference only for presentation of his/her session, that speaker will not be required to register for the conference.   Speakers will receive a specific badge that identifies their registration category: this is to prevent the speaker from going to other sessions, events or meals.  (Just session: no fee and no badge).

The VP of Conferences will have discretion to grant a fee waiver if a speaker is unable to pay the fee. Such waiver requests will be sent directly to the VP of Conferences. The fee waiver decision will be transmitted to the conference event consultant who will coordinate the waiver outcome with the speaker requesting the waiver.

Press Passes

Press attending the conference will be provided with a complimentary Press Pass, but will be required to pay for their hotel expenses and any meals.  The number of press that will be provided complimentary Press Passes must be approved in advance by the VP of Conferences in consultation with the VP of Public Information.  The VP Public Information shall work with the Conference Host Committee so it is aware of press invited and expected to attend the conference, and to ensure the press are greeted, provided session information, and guided to the sessions or events they wish or were asked to attend.  If possible the names of those obtaining press passes should be provided to the Conference Event Consultant who will maintain the list at the Registration area.

Full conference registration shall be provided for the:

- APA California President

- APA California VP of Conferences

- VP of Professional Development

- Conference Host Co-Chairs

- Other complimentary registrations for elected APA California officers must be approved by the VP of Conferences and the Chapter President.  The Chapter will reimburse the conference budget for food costs for these complimentary registrations.

Note: Full conference admission shall be provided for the following APA California staff/consultants:

- APA California Executive Director

- APA California Administrative Director

- APA California Conference Event Consultants

- APA California Registration Consultant

- APA California Attorney

Invited Guests of APA California President

The APA California President may invite four guests from other chapters or from National APA.  These guests will receive complimentary registrations for the basic conference.  If they attend any optional events or mobile workshops, the guests will be responsible for paying for these themselves.

Region VI Board Representative and AICP Commissioner

Full conference registration shall be provided for the National APA Region VI Board representative and AICP Commissioner.

            - Complimentary Hotel Rooms

Complimentary hotel rooms in the main conference hotel shall be provided by the Conference Event Consultant for the length of the conference to the following:

- One presidential or hospitality suite for the APA California President

- One room for the Executive and Administrative Directors

- One room for APA California Conference Event  Consultant

- One room for APA California Public Relations Consultant, but only upon the request of the Vice President, Public Information for the days the VP designates.

- One room (up to four) each for invited guests of APA California President (could include National APA Executive Director, National APA President or others determined by APA California President)

- One room for Region VI Board representative

- One room for Region VI AICP Commissioner

- One room for the VP of Conferences

- One Room for the VP of Professional of Development

- Up to two (2) rooms for the Conference Host Committee Co-Chairs

- One room for Registration Consultant

            - Registration Fees

Minimum Registration Rates

Conference registration rates shall be set to ensure all conference costs and profit requirements are met. The fee will vary based on site location and costs and will be approved by the Board with the approval of the conference budget.

Reduced Conference Rates for Students

Reduced rates will be provided to students at all APA California-sponsored conferences.  The APA California Chapter Board shall decide the amount of the reduction, but the reduced fee at a minimum shall cover food and beverage costs.

Reduced Conference Rates for APA Life Members

Reduced rates will be provided to Life APA members (APA members are eligible for Life Membership after 25 years or more of continuous membership).  The APA California Chapter Board shall decide the amount of the reduction, but the reduced fee at a minimum shall cover food and beverage costs.

Non-Member Membership Registration Option

Registration materials shall provide an option for non-members to sign up as members when they register for the conference.

            - Volunteers

Volunteers will be needed through the conference.  While the Conference Host Committee can ask local section members to assist at the conference if they are not already involved in the CHC, reduced conference registration rates or complimentary registrations are not available to regular APA California members.  .The best source for volunteers are students from the local colleges and universities with Planning Programs.  Because APA California wants students to attend, and the registration costs are sometime prohibitive, the Chapter has reduced student fees to $50 per day.  If a student volunteers  8 hours or more during the conference, half of the full student registration fee is rebated back to the student.

# IV. INSURANCE AND RISK MANAGEMENT AND	MISCELLANEOUS ITEMS

## Catastrophic Insurance

The VP of Administration must obtain catastrophic/conference interruption insurance for the conference to ensure the conference profits is not jeopardized by a disaster such as earthquake or flood.  The VP of Conferences shall contact Accounting Management Consultant to obtain the insurance from the APA California insurance provider.

## Use of Chapter Liability Insurance

Chapter liability insurance covers the conference; however, off-site activities and use of outside vendors or companies are not covered by this insurance.  For information about the Chapter liability insurance, or for proof of insurance required by the conference venue, contact Accounting Management Consultant. The conference must require that transportation companies for mobile workshops or other conference-related events carry their own insurance.

## Conference Activities to be Approved by APA CALIFORNIA Attorney

To ensure that APA California and the Conference Host Committee are not taking inappropriate risks, activities other than those already specified on the APA California liability insurance policy must be reviewed and agreed to by the APA California insurance provider and the APA California attorney.  These activities shall be outlined by the Conference Committee to the APA California Director of Administration as early as possible in the planning process so that the Director can contact the insurance provider for approval (i.e. offsite activities such as opening reception).  All additional insurance contracted for by the Conference Host Committee shall be obtained through the Director of Administration and the APA California Insurance Provider and referred to the APA California attorney for review.

## Association and Section Activity Guidelines

The Conference Host Committee shall also adhere to the legal guidance concerning insurance and activities in the insurance policy listed coverage and the attached Association and Section Activity Guidelines (see Appendix A).

## Disability Inquiries and Complaints

The VP of Conferences, conference event consultant and the Director of Administration shall be the points of contact for the disability inquiries and complaints concerning the conference and conference facilities.

Any Injuries or complaints shall be forwarded to the APA California attorney before responses are provided.

# V.	THE CONFERENCE PROGRAM

Even though the bulk of this manual addresses necessary logistics, the sessions and events presented at the conference are the heart of the conference. The program is a chance to highlight regional assets and local efforts. Because the conference is the largest, most complex, annual activity of the chapter, development of the conference sessions and events is a process led by the Conference Host Committee [CHC] with input from, and approval by, the APA California Board [APA California], including the Vice-President of Professional Development and the Vice-President of Conferences.

The discussions below are grouped by topics within the responsibility of the CHC Programs Committee rather than in chronological order. Programs Committees may find it beneficial to initiate certain tasks earlier rather than later based on number or physical location of committee members, or conference site location.

Also, Appendix H of the manual contains sample forms that can be used by Programs Committees in their session development and review.

## CONFERENCE THEMES & TRACKS

Conference Theme

The conference theme and logo distinguishes your conference from others. The conference theme should be reflective of your region and highlight your local activities and assets. After forming the CHC, these are your earliest tasks.   While the theme is a CHC proposal, the APA California does reserve the right to require the theme to highlight an issue of importance to the entire chapter.  In any case, the selected theme will be subject to APA California approval which may be conducted either at a meeting or by email vote.

The conference logo must include the following:

- APA California or the APA California Logo

- Conference dates

- Location, City and Hotel

- Theme

A complete spec sheet for the Logo can be found in attachment --.

It has been typical that the CHC occupies a complimentary booth at the prior year’s conference to promote the next year’s conference. Therefore, selecting a conference theme and logo and preparing ‘giveaways’ for the prior conference is typically completed about a year prior to your conference. It may be more than a year if your conference is late in the fall [such as November] and may be less than a year if early [September].

Session Tracks

Identification of conference tracks follows theme and logo development. Tracks, used to identify series of similar-subject sessions, should be reflective of the themes of the conference.  Keep the session tracks simple. Remember that the sessions should cover all types of planning as well as be relevant to California’s urban, suburban and rural areas. Typically, no more than 4 or 5 tracks are advised. To help session submitters determine which track they will enter their session in, adding a few descriptive phrases characterizing the subject matter in each track will be helpful.  The online session submittal form contains a list of topics that is used when the Chapter submits the selected sessions to APA National for CM credit. Session submittals will be asked to identify one or more topics from this list as their subject matter. When describing your tracks, make sure that all the topics could be generally accounted for in one of the tracks.

Tracks are important information in the Call for Presentations which is typically published around the time of the prior year’s conference so they should be fully developed by that time, along with the conference theme and logo. See below for Call for Presentations.

“Young Planners” is an emerging session identifier. It is not a track, but is an icon that the host section’s Young Planners Group [YPG] can attach to sessions that they believe are important to planners with 0-5 years experience.   It is recommended that several sessions each year be specifically identified as of particular interest to “Young Planners.”

## CALL FOR PRESENTATIONS & ONLINE SUBMISSION FORMS

The team of the CHC’s Program Committee Chair, the Vice President of Professional Development (or Chapter Programs Coordinator) and Vice President of Conferences will work with the Chapter’s staff and consultants to develop a Call for Presentations (CFP) and a general schedule with all the deadlines related to the [CPF], session solicitation & selection and program sessions set up.

Call for Presentations

The CFP is a write-up that invites speakers to submit proposals to speak at the chapter conference. The CFP is written by the Programs Committee discussing the conference theme and goals and identifying the tracks which will be the guiding framework when selecting regular program sessions for the number of available time slots.

The CFP should be detailed enough to excite potential session submitters. It should not contain detail about what will be required in the online session submittal form. It is typically the length of a printed page with graphic emphasis.  The Conference Design and Publication Consultant can prepare the CFP graphics if not submitted with the CFP language by the CHC.

The CFP should be developed and reviewed just before or soon after the previous year’s conference.  Typically the CFP should be posted about 9 months prior to your conference which means November or December following the prior year’s conference. Regardless of the spacing between your conference and the previous year’s, it’s important to allow some number of weeks for submissions after January 1 of the conference year.  The CFP should allow at minimum a month for submitters to propose sessions through the online submission process. The CFP schedule will be set up in the initial discussion with staff and the consultants soon after the prior year’s conference.

The support team has continued to make improvements in the submittal process and includes advisories to submitters based on issues that have come up in prior years. Several key issues that have been or should be addressed early in the submittal process is what will the registration & fee policy be for non-APA speakers; also moderators must be reminded that they will receive a confirmation email that their session was successfully submitted if it was and that they should follow-up with the identified staff if they do not receive that confirmation.

The CFP should indicate the session length being sought to allow submitters to propose a proper number of speakers or materials to be proposed. While in past years there has been flexibility to set the length of regular sessions at 1.25 or 1.5 hours, 1.5 has become the standard length of a session. This length started when Law and Ethics requirements of 1.5 hours had to be accommodated and it was easier to make all session block lengths the same. Additionally, feedback from panels indicated that the 1.5 hour sessions gave adequate time for in-depth presentations plus audience questions.  Potentially allowing sessions of other lengths – such as 2-part sessions that last 3 hours - must be discussed with the Vice President of Conferences and Vice President of Professional Development prior to any final decision.

Online Session Submissions

The Conference Session Submission Form [CSSF] became an online requirement in 2010. The CSSF allows uniformly-written proposals to be evaluated for inclusion in the conference program. Several specific limitations included in the form are the session abstract length and speaker biography length as well as requiring identification of topics to be covered in the session and CM credit justification.

The CSSF limits the number of speakers that can be identified to 5 per session. Even in 1.5 hour sessions a maximum of 5 is recommended as the number which allows for effective presentations and time for questions and answers from the attendees.

A major reason for standardizing the form content is to allow it to be used to submit to APA National for CM credit evaluation. The form used starting in 2010 was approved by APA National for use and thus eliminates the need for the CHC Programs Committee or the staff team to have to rewrite session submissions to adjust content focus or length.  In 2014 an updated submission form was developed with some standardized information that is required of submitters which allows staff and the Programs Committee easier handling of session proposals.

## REVIEW PROCESS FOR SESSION SELECTION

Selecting regular sessions for the conference is the most significant task taken on by the CHC’s Programs Committee.   The review process begins at the end of the period for accepting session submissions through the online form.

Making Certain an Adequate Number of Proposals are Submitted

Emails reminding potential submitters of the deadline have been used to remind or prompt timely submittals. Emails should be sent to Chapter members following the CFP posting on the Chapter website: the 1st email should be sent at the time of the posting to the website announcing the availability of the CFP; the 2nd email should be sent 1 month before the CFP deadline; and the 3rd email 1 week before that deadline. These are sent out after discussion between the staff and Programs Chair depending on the number of proposals received. Staff will send out these emails and will discuss that year’s timing and content with each annual Program Chair.

If the Programs Committee does not believe an adequate number of session proposals has been received, the deadline may be extended by a couple of weeks. The initial schedule that was developed may have had flexibility built in or can be reviewed to find the flexibility to allow the extension. The support team knows how many submissions have been made by the initial deadline and can actually provide the Programs Chair with a progress report a few weeks before the deadline. How many is ‘enough’? It’s a judgment call, but you will be more comfortable if you can review and consider at least twice as many proposals as you have session slots for [number of regular session blocks x number of rooms]. Note: a significant portion of submittals come in the last week before – or even the day of - the deadline. Don’t panic and keep in touch with staff.

In addition to sessions submitted from individuals around the Chapter, or outside APA California, there are sessions you will be soliciting to fill the regular session slots. There are approximately 20 sessions that are ‘guaranteed’ or ‘mandated’ to be placed within the ‘session block’ structure.  See Mandated Sessions below. Additionally, your committee may have worked to secure a substantial number of Law and Ethics sessions [10 or more Law and several Ethics] to meet the continuing interest from attendees in gaining Law and Ethics CM credits at the annual conference.  Additionally, you may have been urging submittal of the local sessions allocated to the CHC which equate to20% of the total number of regular sessions.  So, you may only be depending on unprogrammed, unsolicited sessions to fill about one-half of the number of regular session slots in your session blocks.

Conference Session Selection Participants

Once it’s been determined that an adequate number of regular session proposals have been received, the Programs Committee chair should set a schedule for the Committee to review all proposals.  Generally, the Programs Committee should allow a minimum of two months to sort through and read the submissions and review, rate, and rank them, followed by assigning them to session slots and rooms.

The selection of conference sessions is a coordinated effort between the Programs Committee and the Chapter. However, given the volume of information being evaluated for quality content and fit with the program theme, there are several reasons why the Chapter defers to the Programs Committee in selecting sessions. First, the volume of information being sorted, reviewed and evaluated is massive; face-to-face meetings of the Programs Committee is probably the best way to make sure that all proposals received are reviewed and fairly discussed. Also, it is the Programs Committee members who are the most familiar with the conference themes and tracks and who know how session proposals provide a balanced and enticing program. The Chapter’s selection representatives – particularly the Vice President of Conferences and the Vice President of Professional Development - will review the selections and proposals of the local Program Committee. These Chapter representatives will be evaluating whether a balanced statewide program is being proposed by the CHC committee in terms of urban-rural; north-south; and topics of statewide significance. They may make changes to the list of sessions selected by the local Programs Committee.

When selecting sessions, the Programs Committee should count the number of available regular session slots to make sure that the number of sessions selected plus all mandatory sessions fit into the number of session block slots available.

Conference Session Selection Process

Proposed sessions are collected online and forwarded to the Chapter’s administrative support team.  The conference assistants will create a numbered matrix of submissions’ titles and moderators for use by the Programs Committee and Chapter that are keyed to the individual online submittals.

Two key factors in selecting regular [i.e., non-keynote, non-student] sessions are: having a clear understanding about filling your session tracks, and how many sessions you will be able to select from those proposed.

NOTE: The following discussion is intended to guide the Programs Committee in approaching the daunting task of reviewing and selecting sessions for your conference. It’s meant as a way to think about your committee’s duties and not meant as a dictate. [Forms are provided in Appendix H to help Programs Committees visualize a review format.]

Balancing Conference Tracks: the Programs Committee may find itself with two competing goals: to select the absolute best proposals for the conference and to generally balance the number selected among your session tracks. If you want to review proposals by track, it’s advisable to still sort the session proposals by topic within the track. By doing this you’ll be able to discover whether multiple tracks are selected for the same topic. If so, it is still likely that the proposals will be similar enough that you’ll want to compare them directly and so you’ll move them to one track location. When you review proposals on the same topic, some things to compare are: number and quality of speakers; balance of perspectives being presented on the subject matter; CM creditworthiness of the material; and breadth of material proposed among the proposals.  Try to not select the same speaker for multiple sessions, especially on similar topics. When reviewing sessions and you find only a moderator and one speaker, consider asking the moderator to add speakers – maybe even from another (unsuccessful) panel.

Some Programs Committees have used their tracks in the Call for Presentations as a way to encourage thinking about submittals in a wide variety of topics but then have found a great imbalance in the number of proposals submitted within each track. That is not a problem if it occurs. Tracks have not been identified in conference program documents in a number of years. If you find yourself with an imbalance, it’s recommended that you proceed to divide proposals by the main topic of the proposal: use the listing in the session submission form to divide proposals into topics.

How many sessions: before you start selecting, it’s important for you to have a good idea about how many regular sessions you’re going to be able to accommodate. Factors are: what is the expected attendance at your conference; how many plenary sessions will you have taking regular session block times; how many session rooms have been contracted for that will adequately accommodate concurrent sessions at the conference site; and how many session blocks can you fit in each of the  conference days.   Discuss these factors and calculate the number of regular sessions you are looking for. Even if you are not prohibited from doing so, strive to avoid using general session breakout rooms [i.e., where meals and keynotes are held] for your regular sessions. Using portions of ballrooms may cause room conversion times that are longer than those that typically used between sessions [15 minutes], causing you to lose valuable session time midday.

Regular sessions are divided into groups - sessions that are mandated by APA California [see below]; local sessions [20% of the total number of regular sessions]; and non-local sessions that fill out and balance your tracks.

Mandated sessions are ones that represent groups within the Chapter that present particular perspectives or opportunities to the broader membership, are topics that the Chapter supports including at every conference, or are mandatory for AICP members. Some sessions are reserved for organizations that are part of APA such as the California Planning Foundation or the California Planning Roundtable. These are sessions that you should be on the lookout for during the review of submittals and remind the responsible parties about deadlines. CPF and CPR sessions tend to be presented on subject matter that is not unique to those organizations, so their session has to be considered along with others submitted on the same topic thus requiring timely submittal.

Identify the total number of regular sessions you can accommodate in your schedule. Account for approximately 15 slots of the total number of session slots based on the session below. Then note that 10 is a reasonable number of Law CM credit sessions to include in the program. Reserve more if you are soliciting multiple Ethics CM credit sessions. Finally 20% of the total number of sessions can be claimed as “local sessions”.  The 20% will equate to a different number depending on your total number of sessions that you are planning based on expected attendance and session room availability.  Refer to this table for an approximate breakdown.

| Current Allocation of “Mandatory Sessions” |  | 2013 Handling | What we might look forward to [Regular Sessions] |  |
| --- | --- | --- | --- | --- |
| Legislative Update/Sande George & VP of Policy & Legislation | 1 | One session for Sande – Law CM [may be part of the 10 solicited Law sessions] | is one of the 10 or more solicited Law sessions | 1 |
| Commission & Boards | 1 | 3 guaranteed as C&B rep wants to attract more C&B | 3 is typicale to provide substance to this growing group | 3 |
| AICP Exam Prep | 1 | Produced by AICP Exam Coordinator/VPPD | Same | 1 |
| Planners Emeritus Network | 1 | One regular session | Same | 1 |
| CPF Sessions | 2 | One regular session + one session on Student Day | Same during regular session scheduling | 1 |
| CPR Sessions | 2 | They requested 3 of their sessions this year | They are a source of competent reliable sessions | 2-3 |
| Ethics | 1 | 3 were proposed this year. | We need to have 3 or 4 for selection | 3-4 |
| Section Directors | 1 | Not in the required list but presented in 2013 | Same | 1 |
| Chapter President | 1 | Not in the require list but has been presented in recent years | Same | 1 |
| Law | 1 | We have about 10 submitted this year, including Sande George/David Snow’s; all were approved for CM Law & for MCLE | We should have 10 for sure in a variety of topic areas we pursue to assure an array of topics. Looking at ‘Law Day’ on Monday | 10 |
| CHC – Local Selection | 20% | They did select 20% | Continue with 20% of total # of regular sessions; if there are 9 session blocks with 8 sessions each = 72 regular sessions typical | 15 |

Trends in several areas of session selection are represented in the above matrix and reflect a goal of attracting new conference attendees such as more Commission & Board members and more attorneys. For example, the idea of an enhanced series of law sessions is attractive to many APA members and also allows the conference to try to attract attorneys who are seeking California MCLE credit [our Law CM sessions typically qualify for MCLE credit from the Bar Association]. Incorporating several guaranteed focused sessions for commission and board members will attract more of them to the conference. These groups may contain APA members or may entice them to become members of APA because of the professional development offerings available.

Note that student sessions are not identified in this matrix. That is because they do not occupy regular session slots which are devote to as many CM creditworthy offerings as possible.

Local sessions can be 20% of the total number of regular sessions at the conference. The identification of a local session can be either one that the CHC feels strong must be included in the program, features local speakers, or highlights accomplishments within the host section’s area. The CHC may want to make its Section members aware of this opportunity and encourage submittal of sessions through the regular CFP submission process. It is NOT mandated that 20% of the sessions MUST be local sessions; conversely if more than 20% of all sessions proposed are from the host section, it does not mean that local sessions must be rejected because they are local. If they are worthy of consideration otherwise, there is nothing to say they cannot be selected as sessions of statewide significance.

Take the total number of regular sessions, then deduct 15 mandated sessions and the number of Law and Ethics sessions you want to include, then deduct 20% of the total number of regular sessions for local selections; the remaining number is how many sessions the Programs Committee should select to balance the program topics and implement your theme and tracks.

When the CHC Programs Committee has selected sessions, or held session slots for mandated sessions not yet received, a list with the numbered session title and session track should be forwarded to the chapter reviewers (the VP of Conferences and VP of Professional Development) for concurrence or modification. This can probably be handled via email, though a meeting or conference call may be easier or convenient. [See Appendix H for a sample listing format of numbered sessions.]

A few more recommendations when selecting sessions: while you are looking for the best presentation on a topic, and may be drawn to a known moderator, don’t select the same speakers for more than several panels; be cautious of sessions that sound good but have only the moderator listed; be cautious of multiple sessions with the same person – not the moderator – listed as the contact: it could mean the contact is a PR person for one or more companies proposing multiple sessions and experience has shown that there may need to be a significant amount of assistance by the conference committee or support team  to get the session information completed and submitted on time.

While some topics continue to be “hot” year to year, others aren’t. Review your session selections against the prior year’s program to make sure that your sessions are not primarily duplicative of them. Recent comments from conference attendees indicate a desire for more variety in topics presented.

## CONFERENCE SESSION NOTIFICATIONS

Following completion of the Programs Committee selection process, AND concurrence by Chapter representatives, notification must be made to both those not selected as well as to those selected.  The CHC Programs Committee will coordinate with the support team by providing the numbers and names of those submissions both selected and not selected and separate notices will be sent to the moderators.

It is suggested that the Programs Committee NOT indicate that a waiting list will be established for those not selected but still interested in presenting their session. Sessions rarely are withdrawn, and if they are, it is done so close to the time of the conference that an alternative panel would not have adequate preparation time.  If a session does drop out, the Programs Committee can probably find a local session to substitute. In general, one session dropping out of a session block does not adversely affect the overall quality or variety of sessions in that block or the conference program overall.

For those sessions selected, the moderator is clearly told that they are the point of contact for staff and the Programs Committee.  The moderator will be contacted about audio-visual information and to confirm the content of their abstract for the program documents and submittal to APA National for CM credit among other things. It is inevitable that some speakers will change, or a topic will change slightly from what is proposed. It may even be that the Programs Committee requests a slight adjustment in a topic to provide what they believe is a more suitable discussion.

The Programs Chair will work with staff to keep in contact with moderators at appropriate times. It’s advisable to keep in regular contact with moderators, updating them as to progress in various areas of conference preparation.  Also, it’s advisable to remind them in each email about certain key points: registration policy for speakers; what A/V equipment will be provided in the room; how and when their panel’s presentation is required electronically.  The Programs Committee chair and support staff should discuss the need for particular emails to moderators depending on how timely responses are given to request for changes or other information. The Programs Chair should work with support staff to prepare the content of the emails, and support staff can email them out. The following emails can be considered:

- following the email regarding their session selection, ask them to confirm that they are still interested in presenting their session;

- after assignment to a particular session block, ask them to confirm that they and their panelists are available at that time and date;

- prior to support staff’s submittal of all eligible sessions to APA National for CM credit, ask moderators to confirm again their title, topic, date and time; [See Section F below on CM credit]

## ORGANIZING THE SCHEDULE & SLOTTING OF ALL THE PROGRAMS

In addition to regular sessions, the conference must accommodate a variety of special events and mandatory sessions and meetings. More frequently, special meetings of APA Divisions, state management, and APA special interest groups are being held at conferences. While it’s important to have an idea of the magnitude of special events at the time of reserving hotel and conference center space, fitting these times with the regular conference sessions to make sure there’s room for all comes together when developing the conference schedule. In general, it is the role of the hired Conference Event Consultant to find time slots and meeting rooms for special [i.e., non-session] meetings. Special meetings will not displace regular session block sessions.

Develop a Schedule Shell

A schedule shell is a figure or diagram that divides each conference day into time slots, starting with breakfast, showing session block timeslots, breaks, luncheons, and evening events. It will help the Programs Committee and CHC to prepare a visual aid to see how regular sessions, required sessions, luncheons, special events, and special meetings will all fit into the conference time slots. Since any schedule will be converted into the format of a ‘Conference at a Glance’, it is easy to start with a schedule blank that is in Glance format. The staff or graphic design consultant will provide the CHC with a typical shell to start. You can get a sense of organization by looking at the one from the prior year’s conference. That does not mean that the timeframes for sessions must be those times, nor does it dictate time or number of keynote sessions. It is simply a format that Board members, the Conference Event Consultant and graphics and other support staff are familiar with. If the CHC and Programs Committee places keynote, general and regular sessions, along with Mobile Workshops, into the Glance, it enables the chapter officials to understand the flow of your conference, and gives a head start to the Graphic Designer who prepares the Glance for posting to the website and, eventually, the program document.

Assigning Individual Sessions to Session Blocks

The assignment of the selected sessions to time slots [session blocks] is a process best done by a handful of Programs Committee members who have reviewed and selected the sessions, perhaps joined by another CHC member who can record where the sessions are placed. The outcome must have each session block with the assigned sessions and their track identified. The graphics design consultant will then be able to take your information and prepare an early version of the Conference at a Glance. Don’t worry about room assignments at this point.

An option for a successful approach: Use a large conference table that can accommodate all your session blocks, or use post-it notes. If you are using tracks to sort, color-coded by track with the session name. You can color-code your session titles by track, then take the first track and distribute its sessions into all your session blocks. You’ll have multiple sessions from the same track in the same session block – just check to make sure you don’t have a very similar topic in the same block. If you decide to sort sessions only by topic, follow the same process to sort the topics into tracks.

After distributing all sessions, go to all the sessions assigned to each session block and make sure you don’t have the same speaker assigned more than once in that block. [Staff can assist with tools that show each speaker and which session/s that speaker is on a panel]. That is something to keep track of until the schedule is published since speakers are sometimes added late or are replaced. Very importantly: you should not place more than one or two major sessions [you know what those are!] in the same session block; spread them and popular sessions among all the session blocks. Also, think about using the most popular sessions as final-day or early morning/late afternoon anchor-sessions to maintain your session attendance numbers.

You just might want to use a blank Glance to display your initial session distribution for easier analysis.

Once you finalize the assignment of your sessions and forward to the Graphic Designer and staff, staff will begin to prepare forms that can be used for submittal for CM credits to APA National. The form contains all the information that was submitted originally by the moderator, plus the day and time that the Programs Committee has assigned. It is that form that is then sent back out to the moderator to confirm title, abstract, moderator, speakers, time and date.

Note that if you are incorporating a concept such as “Law Day” into your program, you’ll want to provide enough Law CM credit sessions [that are also MCLE] through all sessions on one day. However, it would be good for the overall program to have some law sessions on other days. Ethics CM credit sessions are also ones to spread through the conference in case someone can only manage a 1-day registration.

Note also that certain of the “mandatory” sessions involve APA California Board members or staff. Board or other official meetings are sometimes held during regular session blocks. Check with the moderators of these sessions to assure that there are no conflicts for them with the session block you have assigned. For example, the APA California President has official duties at a number of plenary events and if on a session panel immediately before or after a plenary, it can have a negative impact on the individual or the session.

Room Assignments

Review all session block assignments with staff who can help you search and confirm that you have not double-booked a speaker. Once you determine that no more switching of session times will occur, the Programs Committee can assign sessions to rooms. This is an easier assignment if all your session rooms are large and are the same size. Otherwise, take time to think about which are most likely to be popular and put them in the larger rooms. A good way to get a sense of which sessions will be most popular - and therefore deserve the largest rooms - is to have each Programs Committee member predict which 2 or 3 sessions will attract the largest attendance and the smallest attendance in each session block. Compare the answers and order the sessions based on your committee’s attendance estimates. Match the list to the session rooms by their capacities and your room assignments are essentially done!

It may be that the conference event coordinator will/can assign the session block rooms. It’s easier for the coordinator if the rooms sizes are the same or similar. If the coordinator makes the assignments, the Programs Committee still should sort each session block’s sessions by popularity and provide it to the coordinator.

Young Planners Group Sessions

Young Planners are Chapter members who have less than five years of experience and are generally under 35 years old. These are our planners who are looking for learning and training opportunities, particularly at Chapter conferences. In 2009 several sessions were identify as “YPG” sessions, i.e., appropriate mentoring or learning opportunities and nuts & bolts sessions. In 2010, the YPG of the local section identified ~2 sessions per session block as YPG. YPG is an additional identifier for sessions already located in conference session tracks – it is not a separate track.  It is suggested that once the Programs Committee assigns sessions to session blocks that the YPG representative on the CHC be given an opportunity to review the session descriptions and identify sessions within each block as YPG sessions.

Note also that in 2010 a Career Development Center was set up by the YPG and was successful. YPG members solicited seasoned professionals to be available to advise young planners in career choices. The work of the CHC is to help solicit those advisors.

Mandatory Special Events that are the Responsibility of the Chapter or Other Organization

The VP of Conferences or designee must plan for, oversee, and include in the Conference Program Document the following special events:

Awards Ceremony: A suitable event must be planned for presentation of the annual awards during the conference. The planning of the event itself is the responsibility of the Chapter Vice-President of Administration and the State Awards Coordinator/s.  The program and the awards are under his/her direction. The configuration of the stage/head table, etc. is their choice. Details of the program are left up to those individuals.  Location and menu are planned by the CHC. The CHC and Chapter representatives should mutually agree upon the slotting of the event in the conference schedule.

CPF Fundraiser and Auction: Time must be made in the conference schedule for the CPF fundraiser and auction.  The VP of Conferences or designee shall contact the CPF Board Conference Liaison as soon as possible to coordinate these activities. The nature of the fundraiser is determined by the CPF, which is responsible for all arrangement, except for time in the program and designation of a prominent location at the conference which is provided by the Vice-President of Conferences with approval of the CPF Board Conference Liaison.

Student Conference and Student Awards Ceremony: The CHC’s Student Committee chair should work with the CPF Board Representative and the APA California Student Representative to develop and schedule a Student Conference and sessions and Student Awards Lunch to be held the day before the conference sessions typically start. With the 2014 shift of the conference to begin in earnest on Sunday, this sets the Student Day on Saturday. The luncheon is the responsibility of CPF working with the Conference Event Consultant, but developing a series of sessions oriented toward students is the responsibility of the CHC. The interest in an enhanced student program has grown in recent years. With students arriving on Saturday morning, the day can accommodate a student session in the morning, then the luncheon, then concurrent sessions in the afternoon in 1 or 2 session blocks. One of those sessions is traditionally a session produced by CPF. There are some presenters who like to focus on presenting to students or new planners. Involve local universities if they are within your Section and active with APA. The student attendees – about 100 of them, some attending the full conference also – appreciated the variety of sessions. [Note – Student Day is free to students, and if other conference attendees show up that day, they may also sit in on the student sessions.]  The Student Committee needs to coordinate with the Programs Committee to determine if regular sessions and/or the Diversity Summit is being planned on Saturday afternoon: if so, the timing and number of student sessions should be adjusted accordingly. Any regular sessions offered on that day may be attended by the students at no cost – however, the Opening Reception would not be included for students unless they paid to attend.

Diversity Summit: The Membership Inclusion Director will work with the CHC and VP of Conferences to schedule a diversity summit.  It is typically held just prior to the opening reception. The content of the Diversity Summit is the responsibility of Membership Inclusion Directors, and any change in timing of the session should be coordinated with that Director.

Special Events and Responsibility of the CHC

Opening Reception: The CHC in coordination with both the Conference Event Consultant and VP Conferences plans the Opening Reception, keeping in mind the cost of food and entertainment, and the ease of accessibility of the venue. The CHC plays an important role in identifying the theme; style of the opening reception and the Conference Event Consultant works in collaboration with the CHC to assist with the facility details, needs and preparing a cost estimate for the event.   Off-site or elaborate opening receptions must be approved by the APA California Board as part of the conference budget process.

Plenary and Keynote Speakers: The CHC is also responsible for the keynote and plenary speakers, including the luncheon keynote.  Brainstorming about these speakers should start at least a year prior to the conference. The speakers should be knowledgeable and vibrant – capable of being part of the advertising to solicit attendees to the conference. Topics may be planning-related. At least one session is encouraged to be an individual who can address innovation or leadership topics in a field other than planning – though have an appreciation for the profession.  The APA California Board must approve all special events speakers desired by the CHC.

It is highly recommended that the CHC specifically invite local area planning commissioners and board representatives to the plenary session(s) to create an opportunity for the key decision-makers in the planning process to engage with APA as an organization. The recently-established Commission and Board Representative on the Chapter Board plays a key role in soliciting representatives’ attendance.

Don’t schedule too many keynote speakers! For example, if you have a plenary session lasting several hours on the last day of the conference, don’t also schedule a keynote presentation that day. Some conferences have both an opening keynote and a luncheon keynote. The only true expectation is for a luncheon keynote speaker on one of the two full days, with the other luncheon being the Awards Luncheon. Be sure that your keynote speakers are CM credit-worthy in order to attract your AICP members to the session.

Pre-Conference Sessions

In 2013 a new “Pre-Conference Session” program component began with two 6-hour [6 CM] sessions prior to the start of regular conference sessions.  Depending on the overall conference schedule, these pre-conference sessions could be on a day that contains student programs and the Board meeting. Depending on the location, more than two sessions can be developed and accommodated.  To ensure high quality and consistent training, all Pre-Conference Sessions shall be developed by the Chapter, under the supervision of the VP of Professional Development and the VP of Conferences who will know which prior sessions were successful and which subject matter might need to be avoided.  All income, minus expenses, shall go directly to the Chapter.  If the Programs Committee is interested in participating in seeking and developing these sessions, it is a great opportunity for a partnership between the Chapter and the CHC.

The sessions should typically have 6 hours of CM credit which means 7 hours scheduled with a ½ hour lunch and 2 15-minute breaks.  One of the sessions shall focus on leadership and/or management.

FAICP members, CPR members and outside experts are sources of speakers and topics that should be considered.

Required Leadership Meetings

Leadership meetings will occur during the conference but are NOT the responsibility of the Programs Committee. Meeting rooms must be scheduled during the conference for the leadership meetings listed below. The Conference Event Consultant will schedule the time and location of the meetings in coordination with the individual noted below who is responsible for organizing the meeting. These meetings will not pre-empt regular conference session rooms. The time and place of the meetings will be listed in the conference program document. The Conference Event Consultant typically contacts the identified APA California Board member to finalize the title, date and time of the session when all other session moderators are contacted.

The VP of Conferences or designee will act as the liaison and point of contact for the Board and affiliated groups for all conference questions and coordination of affiliated group events. Each affiliated group (CPR, CPF, PEN) is required to appoint a conference liaison who will act as the point of contact for the conference committee (Conference Event Consultant) in setting up group events and activities. If no liaison is appointed, the President of the affiliated group will be the conference liaison.

- APA California Board of Directors. Contact: APA California Administrative Director. This meeting must be scheduled the day of the opening reception.

- California Planning Foundation Board of Directors. Contact: CPF President

- California Planning Roundtable. Contact: Roundtable President

- Planners Emeritus Network. Contact: PEN President

- Chapter Student Representative with Section Student Representatives and Student Conference Attendees. Contact: Chapter Student Representative

- Standing Conference Committee. Contact: President Elect/Immediate Past President

- Professional Development Team Meeting. Contact: VP for Professional Development

- Fellows of the American Institute of Certified Planners Meeting. Contact: VP for Professional Development

- Other Professional Development Activities

- President’s Leadership Reception

## CONFERENCE PROGRAM DOCUMENT

Developing and Finalizing the Program Document

The first piece of the conference program document to be developed and refined is the Conference at a Glance. Once the conference shell is developed and the Programs Committee assigns sessions to session blocks, the Glance begins to be posted to the Chapter website to advertise the conference. Expect that the Glance will undergo many numbered and dated revisions. Each new version of the Glance is posted to the conference portion of the Chapter website. The Graphics Designer will direct you on the timing of your review of the Glance to make sure it is the latest information possible. Room assignments do not have to be made by the time the first Glance is posted to the website.

The next step of program development occurs when the staff provides the Graphic Designer information for each submitted regular session as well as write-ups for keynotes and plenary sessions.  [The Programs Committee should expect to write up the keynote descriptions for not only the program document but also for submittal to APA National for CM credit.]

The effort to finalize the conference program will start about 2 months prior to the conference. All changes, even last minute changes, must be completed 2 weeks prior to the conference.

While the bulk of the program is the daily session-by-session listing, the first part of the program provides important information.  Some of the pieces have probably been written up for Cal Planner articles in the prior year. The Graphics Designer will provide an outline of the information to be included, but program tabs can usually be:

- General Information [details based on your conference; includes [e.g.] registration & exhibitor information and hours, attire, electronic devices, disability advisory, availability of presentations on APA website, local dining options, CM credit info, Law & Ethics offerings, MCLE offerings

- Conference at a Glance

- Highlights - Special Events [based on your conference; includes Mobile Workshops & Keynotes, opening reception, awards luncheon, CPF events, consultant reception, breakfasts, career development center, sustainability discussions]

- Day 1 tab printed with sessions/events that day [day of opening reception]

- Day 2 tab printed with sessions/events that day

- Day 3 tab printed with sessions/events that day

- Day 4 tab printed with sessions/events for closing day

- Sponsor Ads

- Notes & Room Location [always include a site map, not just room layout and names, even if the rooms are located close together.]

- In even numbered years, the awards program should include a list of Californians newly inducted into the Fellows of the American Institute of Certified Planners. The VP for Professional Development will provide this information to VP of Administration.

## SESSION RECORDINGS, ELECTRONIC RETENTION OF PRESENTATIONS, AND THE MOBILE APPLICATION – REVISE PENDING DISCUSSION OF TAPED SESSIONS

The Chapter conference has come into the 21st century. We are primarily electronic, though a printed conference program is given/made available to each attendees upon registration check-in. Some attendees handle all program review, including session selection and speaker bio information, via our Mobile App.

In past years, tapes were made of conference sessions and sold individually or in sets. That practice was discontinued some years ago.  In 2014 there is a pilot program to record a 5-8 sessions and make them available as Distance Education following the conference. Procedures to handle the recording details in future years will be prepared following the 2014 conference and inserted into this section of the manual and an appendix if needed.

See the Webinar Committee Report to the Board for June 2014 for details about the program development.

Printed copies of handouts are no longer allowed at sessions. Communications with moderators will indicate this, and will direct that all presentations be forwarded to APA California staff for posting to the Chapter website following the conference. The acquisition of these presentations is generally successful – staff generally receives a majority of presentations. Some attendees obtain them through direct communication with the presenters.

## CERTIFICATION MAINTENANCE [CM] CREDIT

Because AICP members are seeking to maintain their status by accumulating 32 CM credits in a 2 year period, and because some AICP members depend on conference attendance as their primary, or only, source of CM credit, the bottom line calculation for provision of available CM credit should be a minimum of 16 CM. This is not the total number of CM credits available, it is what an individual can accumulate, at minimum, by attending most or all plenary and regular session blocks.

With few exceptions, each regular session at the annual Chapter conference can be submitted to APA National for CM credit for AICP members.  The few sessions which do not get submitted are aimed at attendees with less experience than required for AICP members, e.g., student sessions; some introductory sessions; the session on how to take the AICP exam.  Keynote and plenary sessions are also submitted. The Awards Luncheon has been alternatively approved and not approved for CM credit so the Chapter has taken the position it will not be submitted.

CM credit is applied for at a 1.0 session hour for 1.0 CM credit. Mobile workshops are submitted for the instructional/touring time as well as travel time to the extent that time can be made instructional. The CM forms are submitted to APA National by staff.

Approval by APA National typically takes about 4-6 weeks, so it is important to finalize sessions and speakers, including mandatory ones, as well as mobile workshops, ahead of this 4-6 week period to give staff time to prepare CM forms for submittal.

In order for APA National to continue to grant CM credit for APA California conference sessions, they require a review from each AICP member evaluating the CM-approved sessions attended. Only one completed form per AICP member for the entire conference is required. It is critical to the continued ability of APA California to provide CM credit-worthy sessions that a substantial number of AICP member fill out the “AICP EVALUATION FORM FOR CM APPROVED SESSIONS”. The CHC should assure that CM Evaluation forms are provided to all AICP members when they register. These forms are anonymous. They should be collected before AICP members leave the conference. An earnest explanation to AICP members about the importance of the form at the conference’s plenary sessions and in writing on the form and in the conference program document seem to get positive results.

Following the conference, a conference committee member should review the forms and summarize pertinent information, particularly to pass on to the next year’s conference committee. Staff will retain the forms for the record and for possible audit by APA National.

## MOBILE WORKSHOPS

Mobile Workshops (MW) are an exciting and critical part of a conference program. The method of selection of MWs is at the CHC discretion. It may be that the CHC brainstorms ideas, comes up with a list, and then solicits section members to lead the workshops, detailing out the tour content and logistics. Or, the CHC can more broadly ask section members for their proposals for MWs.

Mobile workshops should be developed concurrently with the selection of regular sessions.  As soon as your mobile workshops are identified, they can be written up and promoted along with other conference highlights in the Cal Planner.

Since MWs are submitted to APA National at the same time as regular sessions and keynotes are submitted for CM credit, the number of CM being requested must be clear. The MW Coordinator should strive for each MW to have as much learning time as possible – e.g., on the bus if instruction is possible – but ultimately the amount of learning time between the time the attendees board the bus until they disembark must be calculated. Generally, more learning time = more CM = more attendees.

Here are some general guidelines:

- Half-day mobile workshops are preferred to avoid constraints of meals away from the conference site and MW participants possibly having too much non-CM credit time.

- For an all-day [or ‘go-through-lunch’] workshop, it is beneficial – and an advertising opportunity - to have the lunch be sponsored by the proposer. If a sponsor is not an option, the conference will provide a box lunch [either from the hotel or from somewhere on the way] or the moderator can arrange for lunch out on the tour. If you go with that option, be sure to check with the Conference Event Consultant about the maximum $$ that can be spent per attendee.  The cost of the tour will probably need to include the lunch cost.

- Half-day MWs should go out after the opening speaker, if there is one and if possible. More importantly, morning MWs should be back in time to allow attendees to go to the day’s luncheon. Afternoon MWs should return by 5pm or 6pm – depending on the starting time of evening events.

- MW leaders will need to fill out the a session submission form that is the same as those for regular session submitters since CM information is required and a description of the MW is needed for the program.

- MW leaders will need to provide time and transportation requirements to the CHC during the process in order to allow the cost of the MW to be calculated and disclosed in the Early Registration materials. A sample form that can be used for MW tracking and analysis is found in Appendix H.

- All-day or more-than-1/2 day MWs are okay on one of the 2 full days of the conference.  They are preferred on the day of an awards luncheon [vs. on the day of a keynote luncheon].  The all-day MWs should go out after participants have a chance to grab the continental breakfast during its announced time.

- The conference will provide snacks for all MWs.

- Aim for approximately 10 mobile workshops, depending on the conference site. No more than 2 MWs during the same ½ day is recommended.

Keep up email communications with the MW leaders as you do with the session moderators. MW leaders will want to know the status of the signups for their workshops; you will know these numbers as the registration numbers start coming to you from the Conference Event Consultant. For some MWs it’s important to get a sense of whether it will be a large number of attendees or a smaller group. Some MWs may have to set a maximum number of signups if there’s a limit or clearance required from a workshop stop.  See Appendix H for sample emails to MW coordinators.

The Conference Event Consultant with the VP of Conferences can gauge about 30 days prior to the conference, based on early registration, whether a mobile workshop is in danger of being cancelled. It may be that one or more mobile workshops gets cancelled at this time, or at least put on watch, if there are 5 or fewer signups. Note: ~10 signups is a number to keep in mind to know whether a mobile workshop will be feasible – the key being it won’t lose [much] money - given the variety of bus sizes available these days.  The Mobile Workshop Coordinator may want to give a heads up to those individual workshop leaders if there’s a thought that their workshop might be cancelled. Even though it is has been said in emails giving all the coordinators an interim attendance number, the moderators won’t necessarily sense that their own workshop is in danger.

It should be expected that there may be a few signups for mobile workshops with on-site registration, or even at the bus just prior to departure. Some conference attendees have indicated that they routinely wait until they are on-site to sign up for mobile workshops. Try not to turn away those interested in signing up on the spot for a MW until you’re sure that the bus won’t have a seat for them. Unfortunately, sometimes individuals signed up cannot make the MW, and their seat becomes available.

# VI.	ADVERTISING THE CONFERENCE

## Cal Planner (4 to 6 issues per year Electronically produced)

The Design/Graphics/Publication Consultant shall provide a Cal Planner production schedule to the CHC.

The following conference announcements are required to advertise the conference:

- One minimum half-page notice/article announcing the conference, or “Save the Date” notice, in the first Cal Planner issue of the conference year.   The notice/article shall be prepared by the Conference Host Section for approval by the VP of Public Information. The Design/Graphics/Publication Consultant provides timelines for Cal Planner articles.  Articles are sent to the Design/Graphics/Publication Consultant to integrate the conference branding templates. NOTE:  The notice/article shall also be posted on the APA California website

- Registration/conference information shall be published in Cal Planner (optimally one for release prior to early registration and one for release one month prior to the conference). The registration/conference information shall also be posted on the APA California website.

- Pre-registration materials will be published in the Cal Planner.  The VP for  Conferences in consultation with the VP for Administration and Host Section must contact the Cal Planner Design/Graphics/Publication Consultant	to coordinate the timing and number of 	pages of the notices/articles/ads and the conference brochure no later than January of the year of the conference.

- The Spring issue of Cal Planner is the “Conference Issue” and should contain enough information to generate interest in the conference.

It should be noted that notification/e-mail updates can be sent anytime independent of other state publications.

The Cal Planner conference ads will be printed in Cal Planner at no cost to the conference committee but the Conference Host Committee must prepare the text and graphics.

## Section NewsletterS

The VP of Conferences and VP of Public Information shall provide Section Newsletter Editors with conference notices/articles and materials that are to be included in the Section newsletters and on the Section websites.

## APA CALIFORNIA Website – CONFERENCE POSTING PROCESS

The Conference Event Consultant shall work with the VP for Conferences, the Section CHC, and Web Consultant to develop the conference announcement, registration materials, conference registration application, call for papers, articles, and other conference items as determined by the VP of Conferences to be posted to the APA California website.

The following conference announcements must be posted on the APA California website.  These are the same announcements prepared for Cal Planner (see VI. A).

1.	One article announcing the conference, or “Save the Date” notice, in January/February of the year of the conference.

2.	A registration/conference information packet.

## CONFERENCE WEBSITE

The conference website pages are constructed and maintained by the Web Consultant .

## SEND E-mails Directly to APA CALIFORNIA Members

At least two e-mails to members (one early and one final announcement with registration instructions) shall be sent directly to APA California’s members by direct e-mail using the most up to date National e-mail list.  All notices are sent by the Web Consultant to the membership through the APA California website.

The APA California e-mail distribution policy requires e-mails to members to provide the recipient with the opportunity to opt out of future e-mails with an automatic subscribe or unsubscribe option in the e-mail.  E-mails must include the sender’s contact information and postal address.

# VII.	EXHIBIT BOOTHS/DISPLAY SPACE

## Complimentary AND CONTRACTED Display Space

The following receive free display space in the exhibit hall or exhibit space.  Except for the APA California booth and table, which should be visible at or near the entrance to the exhibit hall or exhibit space, the space provided does not need to be premium space, but should be included in the regular exhibit location. Because these agreements are updated frequently, the Conference Event Consultant shall contact the Director of Administration to determine if any other reciprocal agreements have been added or deleted from this list, or updated.

- APA California - (booth and table) - contact Director of Administration

- Following Year’s APA California Conference - (table) - contact Conference Committee chair

- Best, Best & Krieger - (table) - contact APA California Attorney

- AEP - (table) - contact  AEP Executive Director

- APA California Historian – (table) – See Chapter Board roster.

- Cal State Northridge – (table) –  contact Rob Kent at rkent@csun.edu

- Solano Press-(table) – contact Ling-Yen Jones publisher or Nancy Mc Laughlin

- UC Davis Extension – Half price for Table Top in exchange for discount on extension classes.

- UCLA Extension - Conference Ad and Brochures for Land Use and Planning Law Conference placed in unmanned table top area in exchange for 2 free Land Use and Planning Law Conference registrations.

# VIII.	OTHER MANDATORY ITEMS

## ADA COMPLIANCE AND NOTICE IN REGISTRATION	MATERIALS

For ADA compliance, the Conference Committee shall include notice in registration mailers indicating that the conference hotel is ADA compliant and that reasonable accommodations will be made if a registrant provides early indication of needs.

## RESERVE HOTEL ROOMS FOR APA CALIFORNIA BOARD

A block of rooms shall be set aside for Board members and staff at the main conference hotel.  A deadline for confirming these reservations will be established by the Conference Event consultant and the Board and staff informed of the deadline and steps necessary to ensure that they have rooms in the main conference hotel.  The Conference Event Consultant shall request that the hotel provide upgrades (view, suites, and larger rooms) for Board members’ rooms.

## EXTRA HOTEL ROOMS

The Conference Event Consultant shall reserve an additional five rooms for unanticipated guests, press or last-minute Conference Committee use.

## REGISTRATION CONFIRMATION

Conference registrants must be sent a written confirmation within a reasonable time of receipt of their registration.  The confirmation can be sent via e-mail or regular mail.

# IX.	MOBILE APP

The current point person for the mobile app is the Accounting Management Consultant/Web Consultant.

The Roles of the Point Person are:

- Manages timeline

- Central point of contact with Mobile App provider

- Collects key information from managers

- Works directly in GD Online Dashboard

The other part of the process that needs to be done upfront is to register APA California with Apple.  Apple now requires that apps are submitted under the client’s account.  Below is a document that describes that process, which takes a week or so.  Apple requires that the registering entity assign one person in charge of the Apple account, which Apple calls the “Agent”.  The Apple Agent currently is the Accounting Management Consultant/Web Consultant.

# X. AT THE CONFERENCE

## THANK THE CONFERENCE COMMITTEE

The Conference Host Committee shall be officially introduced and thanked during at least one major conference event.

## HEAD TABLE FOR APA CALIFORNIA BOARD

At least once during the conference there must be an opportunity for the APA California Board to be introduced to the membership. This is generally done by seating the APA Executive California Board at a head table during a plenary lunch or session or simply by having the Executive Board members stand up during a lunch or event.

The Board members shall be notified by the VP of Conferences at the Board meeting when they will be expected to be at the head table (or other event where they will be introduced or play a part).  The VP of Conferences will coordinate which Board members will be in attendance so that the head table can be set to seat only those who will be present.

## APA CALIFORNIA BOARD REGISTRATION PACKET DISTRIBUTION

The Conference Event Consultant shall provide the APA California Board members’ and staff with their registration packets sometime during the APA California Board meeting.

## RIBBONS FOR NAME BADGES FOR LEADERSHIP AND SPEAKER IDENTIFICATION

Different colored ribbons or other identification shall be provided at registration, to be attached to the badges to recognize individuals such as:

- Conference Host Committee members

- APA California Board members

- California Planning Foundation Board members

- Planners’ Emeritus Network Board members

- California Planning Roundtable Board members

- Speakers

- Students

- Planning Commissioners

- Award winners

- Staff (when staff are also speakers, they should be provided with both ribbons)

- National Board members

A comprehensive list can be found in Appendix XX.

# XI.  STANDING CONFERENCE COMMITTEE

The Standing Conference Committee is chaired by the President and is composed of the following members: Host Chair of the previous year’s conference; Host Chair of the current year’s conference; Host Chair of the following year’s conference; President Elect/Immediate Past President; Vice President for Conferences; Executive Director, and Director of Administration.

This Committee shall meet during the conference each year or within one month following the conference to facilitate coordination between various years’ conference committees, to discuss issues related to the annual conference and to review Board Conference Requirements and make any recommendations it deems necessary concerning the Requirements or other conference policies to the Board.

The Standing Conference Committee shall meet by conference call during the year as necessary to keep the Conference Handbook updated and the Conference on track.

XII. UPDATING AND DISTRIBUTING THE CONFERENCE HANDBOOK

## VP of CONFERENCES

Within three months following the conference, the VP of Conferences shall:

- PROGRAM.  Add the conference program to the official Conference Binder.

- CONFERENCE SUMMARY.  Provide a summary of the Conference, including the budget, how many rooms were used at the conference hotel, conference attendance broken down by registration categories, and the attendance at specific conference events and mobile workshops.

- RECOMMENDATIONS TO THE BOARD AND STANDING CONFERENCE COMMITTEE.  Make recommendations to the Board and Standing Conference Committee concerning changes or clarifications to the policies contained in the APA California Board Conference Requirements Handbook. The APA California Board shall approve any changes made to the APA California Board Conference Requirements Handbook.

## STANDING CONFERENCE COMMITTEE

The Standing Conference Committee shall be responsible for collecting input and updating the Handbook and distributing the updated Conference Handbook to the upcoming Conference Committee. All major changes to the Handbook shall be approved by the Board.

## PRESIDENT AND VP CONFERENCES

The APA California President and Vice President of Conferences shall be authorized to make interpretations and minor amendments to the manual without Board approval.

## APA CALIFORNIA BOARD

All major changes to the APA California Conference Handbook Board Conference Requirements shall be approved by the APA California Board.

# Conference Handbook Timing Roadmap

[In progress. To be updated October 2014]

# Glossary of General and Conference Related Terms

[In progress. To be updated October 2014]